## Sheet1
COSC1076 ¦ Semester 1 2021
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | ideabullet
Group Member: | Dunith Nadvi Karawita |  | Progress Classes: | Ahead
Group Member: | Matthew Radin |  |  | On-track
Group Member: | Trang Nguyen |  |  | Behind
Group Member: | You Chan Lee |  |  | Way Behind
Tutor: | Steven
Class: | Thursday 1:30pm
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Dunith Nadvi Karawita | Matthew Radin | Trang Nguyen | You Chan Lee
|  | On-track | Group Formed |  | Weekly Contribution | 25% | 25% | 25% | 25%
|  | On-track | MS Team created |  | Issues
|  | On-track | Git Repo created |  | Other Notes
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Dunith Nadvi Karawita | Matthew Radin | Trang Nguyen | You Chan Lee
|  | On-track | Choice of where to use linked list, vector & array |  | Weekly Contribution
|  | On-track | Initial Design of ADTs (classes and potential methods) |  | Issues |  | Design discussion |  | Design discussion
|  | On-track | Main menu |  | Other Notes |  |  |  | Implemented main menu
|  | On-track | User Prompt (for gameplay), but no/minimal error checking | [5 empty] | Implemented
|  | On-track | Linked List implementation | [5 empty] | Implemented Single-LinkedList
|  | On-track | Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required |  |  | Implemented ADT wraper | Attempted code, code not added, aided discussion |  | Implemented 2D Vector for board
|  | On-track | ADT implementation for storing information, game loop logic not required |  |  | Implemented |  |  | Implemented
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | Dunith Nadvi Karawita | Matthew Radin | Trang Nguyen | You Chan Lee
|  | On-track | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution | Implemented TileBag, Hand class |  |  | Done
|  | On-track | Initialisation of data strctures for new game |  | Issues |  |  |  | Done
|  | On-track | Write Tests Cases for common uses |  | Other Notes |  |  |  | Creates test cases
|  | On-track | Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic |  |  | Done |  |  | Done
|  | Progress | On-track
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | Dunith Nadvi Karawita | Matthew Radin | Trang Nguyen | You Chan Lee
|  | On-track | Fully complete implementation and error free |  | Weekly Contribution |  |  |  | Tested
|  | On-track | Full error checking of user prompt |  | Issues |  |  |  | Tested
|  | On-track | Automated placement of tiles at end of round, but no scoring |  | Other Notes |  |  |  | Tested
|  | On-track | Final Tests |  |  | Did final test | added group work techniques |  | Did final test
|  | On-track | Group Report Written |  |  | Wrote group report |  |  | Modified group report
|  | Progress | On-track